## Gantt 3.0
GANTT CHART
The Drive By Project | [5 empty] | Mohammed, Dirk and Erik | [16 empty] | 2022-02-11 |  |  |  |  | 2022-05-01
PROJECT NAME | [5 empty] | CLIENTS NAME | [16 empty] | START DATE |  |  |  |  | END DATE
Task ID | Task Names | Start Date | End Date | Duration (In Days) | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-01-03 | 2022-02-03 | 2022-03-03 | 2022-04-03 | 2022-05-03 | 2022-06-03 | 2022-07-03 | 2022-08-03 | 2022-09-03
1) | Software modules
T01 | Phototransistors and infrared sensor | [30 empty] | Key
T02 | Rubber band gun | [31 empty] | Done
T03 | Seven segment display | [31 empty] | Little to no progress
T04 | Motor Control | [31 empty] | Not Started yet
T05 | Comparator Buffer | [31 empty] | Halfway done
2) | Hardware
T05 | Phototransistors and infrared sensor
T06 | Rubber band gun
T07 | Seven segment display
T08 | Comparator Buffer
3) | Overhead
T09 | Presentations | 2022-02-14 | 2022-02-16 | 3 |  |  |  | 1 | 1 | 1
T10 | Budget charts | 2022-02-14 | 2022-02-16 | 3 |  |  |  | 1 | 1 | 1
T11 | Gantt charts | 2022-02-14 | 2022-02-16 | 1 |  |  |  | 1 | 1 | 1
T12 | CPR Certifications | 2022-02-11

## ©
© TemplateLab.com