## Overall Budget
Project Lab 1 | Running Total |  |  | Total Estimate |  |  | Start Date | 2022-01-12
Direct Labor(DL): | [6 empty] | Today | 2022-01-26
Category/Indvidual | Rate/Hour | Hours | Total | Rate/Hour | Hours | Total
Dirk Thieme | 15 | 27 | 405 | 15 | 70 | 1050 | End Date | 2022-02-09
Erik Manis | 15 | 27 | 405 | 15 | 70 | 1050
Mohammed Santari | 15 | 27 | 405 | 15 | 70 | 1050
DL Subtotal: |  | Subtotal: | 1215 |  | Subtotal: | 3150
Labor Overhead | Rate: | 100% | 1215 | Rate: | 100% | 3150
Total Direct Labor(TDL) |  |  | 2430 |  |  | 6300 |  | Key
Current
Contract Labor | [7 empty] | Estimate
Lab Assistant | 40 | 0 | 0 | 40 | 5 | 200 |  | Totals
Classmates | 15 | 0 | 0 | 15 | 5 | 75
Instructor | 200 | 0 | 0 | 200 | 5 | 1000
Total Contract Labor(TCL) |  |  | 0 |  |  | 1275
Direct Material Costs(DMC): |  |  | 224.86 |  |  | 543.21
(Material Cost Spreadsheet)
Total DMC: |  |  | 224.86 |  |  | 543.21
Equipment Rental Costs: | Value | Rental Rate |  | Value | Rental Rate |  | Total Rental Days to Date |  | Estimate Rental Days
Oscilloscope | 449.99 | 0.2% | 4.4999 | 449.99 | 0.2% | 8.9998 | 5 |  | 10
DMM | 415 | 0.2% | 4.15 | 415 | 0.2% | 8.3
Total Rental Costs(TRC) |  |  | 8.6499 |  |  | 17.2998
Total TDL+TCL+DMC+TRC |  |  | 2663.5099 |  |  | 8135.5098
Business Overhead |  | 45% | 1198.5795 |  | 45% | 3660.9794
Total Cost |  | Current | 3862.0894 |  | Estimate | 11796.4892

## Labor Hours
Date | Dirk | Erik | Mohammed | Lab Assistant | Classmate | Instructor |  | Total Hours
2022-01-12 | 3 | 3 | 3 | 0 | 0 |  | Wednesday | Dirk | 27
2022-01-13 | 0 | 0 | 0 | 0 | 0 |  | Thursday | Erik | 27
2022-01-14 | 0 | 0 | 0 | 0 | 0 |  | Friday | Mohammed | 27
2022-01-15 | 0 | 0 | 0 | 0 | 0 |  | Saturday | Lab Assistant | 0
2022-01-16 | 3 | 3 | 3 | 0 | 0 |  | Sunday | Classmate | 0
2022-01-17 | 3 | 3 | 3 | 0 | 0 |  | Monday | Instructor | 0
2022-01-18 | 0 | 0 | 0 | 0 | 0 |  | Tuesday
2022-01-19 | 6 | 6 | 6 | 0 | 0 |  | Wednesday
2022-01-20 | 0 | 0 | 0 | 0 | 0 |  | Thursday
2022-01-21 | 0 | 0 | 0 | 0 | 0 |  | Friday | Key
2022-01-22 | 0 | 0 | 0 | 0 | 0 |  | Saturday | Totals
2022-01-23 | 3 | 3 | 3 | 0 | 0 |  | Sunday
2022-01-24 | 0 | 0 | 0 | 0 | 0 |  | Monday
2022-01-25 | 3 | 3 | 3 | 0 | 0 |  | Tuesday
2022-01-26 | 6 | 6 | 6 | 0 | 0 |  | Wednesday
2022-01-27 | [6 empty] | Thursday
2022-01-28 | [6 empty] | Friday
2022-01-29 | [6 empty] | Saturday
2022-01-30 | [6 empty] | Sunday
2022-01-31 | [6 empty] | Monday
2022-02-01 | [6 empty] | Tuesday
2022-02-02 | [6 empty] | Wednesday
2022-02-03 | [6 empty] | Thursday
2022-02-04 | [6 empty] | Friday
2022-02-05 | [6 empty] | Saturday
2022-02-06 | [6 empty] | Sunday
2022-02-07 | [6 empty] | Monday
2022-02-08 | [6 empty] | Tuesday
2022-02-09 | [6 empty] | Wednesday

## Material Costs
Name | Cost | Quantity | Note/Website | Purchase Date | Total | Total
Rover | 49.95 | 1 | Pololu.com |  | 49.95 | 224.86
H-Bridge | 4.67 | 1 | Mouser.com |  | 4.67
BASYS3 | 149 | 1 | Mouser.com |  | 149
Battery Pack | 3.3 | 1 |  |  | 3.3
Connectors | 3.95 | 1 | Digikey.com |  | 3.95
Charger | 13.99 | 1 | Amazon.com |  | 13.99 | Key
[5 empty] | 0 | Totals
0
0
0
0
0
0
0
0
0
0
0
0
0