## Overall Budget
Project Lab 1 | Running Total |  |  | Total Estimate |  |  | Start Date | 2022-02-09
Direct Labor(DL): | [6 empty] | Today | 2022-02-17
Category/Indvidual | Rate/Hour | Hours | Total | Rate/Hour | Hours | Total
Dirk Thieme | 15 | 33 | 495 | 15 | 160 | 2400 | End Date | 2022-05-01
Erik Manis | 15 | 33 | 495 | 15 | 160 | 2400
Mohammed Ansari | 15 | 30 | 450 | 15 | 160 | 2400
DL Subtotal: |  | Subtotal: | 1440 |  | Subtotal: | 7200
Labor Overhead | Rate: | 100% | 1440 | Rate: | 100% | 7200
Total Direct Labor(TDL) |  |  | 2880 |  |  | 14400 |  | Key
Current
Contract Labor | [7 empty] | Estimate
Lab Assistant | 40 | 0 | 0 | 40 | 15 | 600 |  | Totals
Classmates | 15 | 0 | 0 | 15 | 15 | 225
Instructor | 200 | 0 | 0 | 200 | 15 | 3000
Total Contract Labor(TCL) |  |  | 0 |  |  | 3825
Direct Material Costs(DMC): |  |  | 354.38 |  |  | 543.21
(Material Cost Spreadsheet)
Total DMC: |  |  | 354.38 |  |  | 543.21
Equipment Rental Costs: | Value | Rental Rate |  | Value | Rental Rate |  | Total Rental Days to Date |  | Estimate Rental Days
Oscilloscope | 449.99 | 0.2% | 0 | 449.99 | 0.2% | 26.9994 | 0 |  | 30
DMM | 415 | 0.2% | 0 | 415 | 0.2% | 24.9
Power Supply | 99.99 | 0.2% | 0 | 99 | 0.2% | 5.94
Soldering Iron | 99.99 | 0.2% | 0 | 99 | 0.2% | 5.94
Total Rental Costs(TRC) |  |  | 0 |  |  | 51.8994
Total TDL+TCL+DMC+TRC |  |  | 3234.38 |  |  | 18820.1094
Business Overhead |  | 55% | 1778.909 |  | 55% | 10351.0602
Total Cost |  | Current | 5013.289 |  | Estimate | 29171.1696

## Labor Hours
Date | Dirk | Erik | Mohammed | Lab Assistant | Classmate | Instructor |  | Total Hours
2022-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | Friday | Dirk | 33
2022-02-12 | 0 | 0 | 0 | 0 | 0 | 0 | Saturday | Erik | 33
2022-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | Sunday | Mohammed | 30
2022-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | Monday | Lab Assistant | 0
2022-02-15 | 6 | 6 | 6 | 0 | 0 | 0 | Tuesday | Classmate | 0
2022-02-16 | 3 | 3 | 3 | 0 | 0 | 0 | Wednesday | Instructor | 0
2022-02-17 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-02-18 | 0 | 0 | 0 | 0 | 0 | 0 | Friday
2022-02-19 | 3 | 3 | 3 | 0 | 0 | 0 | Saturday
2022-02-20 | 6 | 6 | 3 | 0 | 0 | 0 | Sunday | Key
2022-02-21 | 0 | 0 | 0 | 0 | 0 | 0 | Monday | Totals
2022-02-22 | 3 | 3 | 3 | 0 | 0 | 0 | Tuesday
2022-02-23 | 3 | 3 | 3 | 0 | 0 | 0 | Wednesday
2022-02-24 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-02-25 | 0 | 0 | 0 | 0 | 0 | 0 | Friday
2022-02-26 | 0 | 0 | 6 | 0 | 0 | 0 | Saturday
2022-02-27 | 0 | 6 | 0 | 0 | 0 | 0 | Sunday
2022-02-28 | 6 | 0 | 0 | 0 | 0 | 0 | Monday
2022-03-01 | 3 | 3 | 3 | 0 | 0 | 0 | Tuesday
2022-03-02 | 0 | 0 | 0 | 0 | 0 | 0 | Wednesday
2022-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-03-04 | 0 | 0 | 0 | 0 | 0 | 0 | Friday
2022-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | Saturday
2022-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | Sunday
2022-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | Monday
2022-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | Tuesday
2022-03-09 | 0 | 0 | 0 | 0 | 0 | 0 | Wednesday
2022-03-10 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-03-11 | 0 | 0 | 0 | 0 | 0 | 0 | Friday

## Material Costs
Name | Cost | Quantity | Note/Website | Total | Total
Rover | 49.95 | 1 | Pololu.com | 49.95 | 354.38
H-Bridge | 4.67 | 1 | Mouser.com | 4.67
BASYS3 | 149 | 1 | Mouser.com | 149
Battery Pack | 13.3 | 1 |  | 13.3
Connectors | 3.95 | 1 | Digikey.com | 3.95
Charger | 13.99 | 1 | Amazon.com | 13.99 | Key
Arduino starter kit | 38.99 | 1 | Amazon.com | 38.99 | Totals
3D printed parts | 30 | 1 | Maker Space | 30
Servo Motors (5) | 13 | 1 | Amazon.com | 13
Phototransistors (10) | 3.74 | 1 | Mouser.com | 3.74
Infrared Sensors (10) | 8.79 | 1 | Amazon.com | 8.79
Actuator | 25 | 1 | Mouser.com | 25
0
0
0
0
0
0
0
0