## Sheet1
Gantt Chart
The Drive By Project |  |  | Dirk, Erik, and Mohammed
Task ID | Task Names | Percent | Week1 | Week 2 | Week 3 | Week 4 | Week 5 | Week6 | Week7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| Software | [14 empty] | Key
1 | Pathing Module | 0% | [14 empty] | Week Completed
2 | Sensing Module | 0% | [14 empty] | No Progress
3 | Camera | 0%
4 | Remote Control | 0%
5 | Radio Transmiton | 0%
6 | Infrared Sensor | 0%
7 | Phototransistors | 0%
8 | State Machine | 0%
9 | Comparator | 0%
10 | Flow Charts | 0%
Hardware
11 | Parts Research | 0%
12 | Phototransistors | 0%
13 | Infrared Sensor | 0%
14 | Camera | 0%
15 | PCB Circuit Simulation | 0%
16 | PCB Circuit Design | 0%
17 | Circuit Schematics | 0%
18 | Radio Transmition | 0%
19 | Simulations in LTSpice | 0%
20 | Comparator Buffer | 0%
21 | Assembly | 0%
Overhead
22 | Presentations | 0%
23 | Budget Charts | 0%
24 | Gantt Charts | 0%
25 | Obtaining Parts | 0%