## Budget
Parts Catalog |  |  |  | Hours Worked | 2022-01-16 | 2022-01-22 | 2022-01-28 | 2022-02-03 | 2022-02-09 | 2022-02-15 | 2022-02-21 | 2022-02-27 | 2022-03-05 | 2022-03-11 | 2022-03-17 | 2022-03-23 | 2022-03-29 | 2022-04-04 | 2022-04-10 | 2022-04-16 | 2022-04-22 | 2022-04-28 | 2022-05-04 | Total | Total Pay
Part Name | Quantity | Price | Running Total | Dirk | 6 | [18 empty] | 6 | 90
BASYS 3 Board | 1 | 149.99 | 156.98 | Mohammed | 3 | [18 empty] | 3 | 45
L289 H Bridge | 1 | 6.99 |  | Erik | 3 | [18 empty] | 3 | 45
180
Tool Rental
|  |  |  | Tool | Days Used | Price | Total
|  |  |  | Oscilloscope | 14 | 5000 | 1400
|  |  |  | Soldering Iron | 14 | 100 | 28
|  |  |  | Multimeter | 14 | 100 | 28
0
0
0
0
0
0
1456
Running Total of all money spent
|  |  |  | 55 Percent Overhead | 986.139
|  |  |  | Final Total | 2779.119

## Gantt
Gantt Chart
| Start Date | Duration
Meet for first time and discuss the gameplan | 2022-01-15 | 5
Order parts for the project | 2022-01-20 | 5
Discuss how to physcially design the device and begin | 2022-01-25 | 7
Create Verilog code to run device | 2022-02-01 | 7
Add finishing touches and present Feb. 9 | 2022-02-08 | 2

## New Gantt
Week | 1 | 2 | 3 | 4
Task List |  |  |  |  | Key
1) Meet up and decide on a plan |  |  |  |  | Color | Meaning
2) Order Parts for the mini project |  |  |  |  | Red | Little to no progress
3) Finish desgining the hardware aspect of the project |  |  |  |  | Yellow | Halfway done
4) Finish programming the project with verilog |  |  |  |  | Green | Almost or completely done
5) Add finishing touches and be done |  |  |  |  | Grey | To be done later on
[5 empty] | White | Already done