## Gantt 3.0
GANTT CHART
The Drive By Project |  |  |  |  | Mohammed, Dirk and Erik | [11 empty] | 2022-02-11 | 2022-05-10
PROJECT NAME |  |  |  |  | CLIENTS NAME | [11 empty] | START DATE | END DATE
Task ID | Task Names | Start Date | End Date | 2/9 - 2/15 | 2/16 - 2/22 | 2/23 - 3/1 | 3/2 - 3/8 | 3/9 - 3/15 | 3/16 - 3/22 | 3/23 - 3/29 | 3/30 - 4/5 | 4/6 - 4/12 | 4/13 - 4/19 | 4/20 - 4/26 | 4/27 - 5/3 | 5/4 - 5/10
1) | Software
T01 | Pathing Module | 2022-03-24 | 2022-03-29 | [15 empty] | Key
T02 | Sensing Module
T03 | Shooting module | [18 empty] | Finished what had been planned
T04 | Seven segment display | 2022-02-23 | [17 empty] | Little Progress
T05 | Servo motor | 2022-02-16 | [17 empty] | No Progress
T06 | Flow Charts | 2022-02-09 | [17 empty] | Some Progress
T07 | infrared sensor | 2022-03-16 | 2022-03-29
T08 | Phototransistors | 2022-05-02
T09 | State Machine setup
T10 | Comparator Buffer | 2022-02-09
2) | Hardware
T11 | Phototransistors | 2022-05-02
T12 | infrared sensor | 2022-06-02
T13 | Rubber band gun | 2022-03-29
T14 | PCB Circuit simulation | 2022-02-17
T15 | PCB Circuit design | 2022-03-23
T16 | Circuit schematics | 2022-02-12
T17 | Actuator | 2022-04-11
T18 | Simulations in LTSpice and EasyEDA | 2022-02-18
T19 | Comparator Buffer | 2022-02-09
3) | Overhead
T20 | Presentations | 2022-02-14
T21 | Budget charts | 2022-02-14
T22 | Gantt charts | 2022-02-14
T23 | CPR Certifications | 2022-02-11
T24 | Obtaining Parts

## ©
© TemplateLab.com