## Overall Budget
Project Lab 1 | Running Total |  |  | Total Estimate |  |  | Start Date | 2022-01-12
Direct Labor(DL): | [6 empty] | Today | 2022-01-26
Category/Indvidual | Rate/Hour | Hours | Total | Rate/Hour | Hours | Total
Dirk Thieme | 15 | 72 | 1080 | 15 | 70 | 1050 | End Date | 2022-02-09
Erik Manis | 15 | 71 | 1065 | 15 | 70 | 1050
Mohammed Ansari | 15 | 66 | 990 | 15 | 70 | 1050
DL Subtotal: |  | Subtotal: | 3135 |  | Subtotal: | 3150
Labor Overhead | Rate: | 100% | 3135 | Rate: | 100% | 3150
Total Direct Labor(TDL) |  |  | 6270 |  |  | 6300 |  | Key
Current
Contract Labor | [7 empty] | Estimate
Lab Assistant | 40 | 0 | 0 | 40 | 5 | 200 |  | Totals
Classmates | 15 | 0 | 0 | 15 | 5 | 75
Instructor | 200 | 0 | 0 | 200 | 5 | 1000
Total Contract Labor(TCL) |  |  | 0 |  |  | 1275
Direct Material Costs(DMC): |  |  | 288.34 |  |  | 543.21
(Material Cost Spreadsheet)
Total DMC: |  |  | 288.34 |  |  | 543.21
Equipment Rental Costs: | Value | Rental Rate |  | Value | Rental Rate |  | Total Rental Days to Date |  | Estimate Rental Days
Oscilloscope | 449.99 | 0.2% | 6.2999 | 449.99 | 0.2% | 8.9998 | 7 |  | 10
DMM | 415 | 0.2% | 5.81 | 415 | 0.2% | 8.3
Power Supply | 99.99 | 0.2% | 1.3999
Soldering Iron | 99.99 | 0.2% | 1.3999
Total Rental Costs(TRC) |  |  | 14.9096 |  |  | 17.2998
Total TDL+TCL+DMC+TRC |  |  | 6573.2496 |  |  | 8135.5098
Business Overhead |  | 45% | 2957.9623 |  | 45% | 3660.9794
Total Cost |  | Current | 9531.2119 |  | Estimate | 11796.4892

## Labor Hours
Date | Dirk | Erik | Mohammed | Lab Assistant | Classmate | Instructor |  | Total Hours
2022-01-12 | 3 | 3 | 3 | 0 | 0 | 0 | Wednesday | Dirk | 72
2022-01-13 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday | Erik | 71
2022-01-14 | 0 | 0 | 0 | 0 | 0 | 0 | Friday | Mohammed | 66
2022-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | Saturday | Lab Assistant | 0
2022-01-16 | 3 | 3 | 3 | 0 | 0 | 0 | Sunday | Classmate | 0
2022-01-17 | 3 | 3 | 3 | 0 | 0 | 0 | Monday | Instructor | 0
2022-01-18 | 0 | 0 | 0 | 0 | 0 | 0 | Tuesday
2022-01-19 | 6 | 6 | 6 | 0 | 0 | 0 | Wednesday
2022-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-01-21 | 0 | 0 | 0 | 0 | 0 | 0 | Friday | Key
2022-01-22 | 3 | 3 | 3 | 0 | 0 | 0 | Saturday | Totals
2022-01-23 | 3 | 3 | 3 | 0 | 0 | 0 | Sunday
2022-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | Monday
2022-01-25 | 3 | 6 | 6 | 0 | 0 | 0 | Tuesday
2022-01-26 | 6 | 6 | 6 | 0 | 0 | 0 | Wednesday
2022-01-27 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-01-28 | 0 | 0 | 0 | 0 | 0 | 0 | Friday
2022-01-29 | 3 | 3 | 3 | 0 | 0 | 0 | Saturday
2022-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | Sunday
2022-01-31 | 3 | 3 | 3 | 0 | 0 | 0 | Monday
2022-02-01 | 3 | 3 | 6 | 0 | 0 | 0 | Tuesday
2022-02-02 | 6 | 6 | 3 | 0 | 0 | 0 | Wednesday
2022-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | Thursday
2022-02-04 | 6 | 3 | 3 | 0 | 0 | 0 | Friday
2022-02-05 | 6 | 5 | 0 | 0 | 0 | 0 | Saturday
2022-02-06 | 3 | 3 | 3 | 0 | 0 | 0 | Sunday
2022-02-07 | 3 | 3 | 3 | 0 | 0 | 0 | Monday
2022-02-08 | 6 | 6 | 6 | 0 | 0 | 0 | Tuesday
2022-02-09 | 3 | 3 | 3 | 0 | 0 | 0 | Wednesday

## Material Costs
Name | Cost | Quantity | Note/Website | Purchase Date | Total | Total
Rover | 49.95 | 1 | Pololu.com |  | 49.95 | 288.34
H-Bridge | 4.67 | 1 | Mouser.com |  | 4.67
BASYS3 | 149 | 1 | Mouser.com |  | 149
Battery Pack | 13.3 | 1 |  |  | 13.3
Connectors | 3.95 | 1 | Digikey.com |  | 3.95
Charger | 13.99 | 1 | Amazon.com |  | 13.99 | Key
Arduino starter kit | 38.99 | 1 | Amazon.com |  | 38.99 | Totals
3D printed parts | 14.49 | 1 | Maker Space |  | 14.49
0
0
0
0
0
0
0
0
0
0
0
0